Workforce Race Equality Standard: Improvement Plan 2018 - 2019

|  | WRES Indicator | Our data for 2018 | Actions | Success Criteria | Responsible Officer | Timescale |
| --- | --- | --- | --- | --- | --- | --- |
| 1 2 | Percentage of staff in each of the AfC bands 1-9 and VSM Compared with the percentage of staff in the overall workforce Relative likelihood of staff being appointed from shortlisting across all posts. | White staff are 1.88 times more likely to be appointed from shortlisting than BME staff | - Continue to hold recruitment events in the local communities we serve encouraging applicants from all communities - Continue with values based interviewing addressing avoiding unconscious bias – target those who have not attended new-style training and set up a system whereby all new Managers/Supervisors get automatically enrolled at the time of commencement in role - Revisit the process mapping for our recruitment process and think about the problems that could be impacting on the likelihood of BME candidates being appointed from shortlisting | Ensure all Recruiting Managers have attended Values based interviewing training Narrow the gap in the relative likelihood of white staff being appointed compared to BME | Resourcing Lead Resourcing Lead | Completed by December 2018 Completed by December 2018 Completed by February 2019 |

|  | WRES Indicator | Our data for 2017 | Action | Success Criteria | Responsible Officer | Timescale |
| --- | --- | --- | --- | --- | --- | --- |
| 5, 6, 7 & 8 | National NHS Staff Survey indicators relating to the experience of BME staff compared to white staff | 37% BME staff report harassment, bullying or abuse from staff 725% of BME staff have personally experienced discrimination at work from Manager/team leader or other colleague. 75% of BME staff believe the Trust provides career progression or promotion | - Support the implementation of the Equality, Diversity and Human Rights Strategy. In particular creating a safe place where staff can speak out and promote equality and diversity. - Develop the work with the Freedom to Speak up Guardian on a campaign to encourage staff to speak out if they experience harassment, bullying or abuse at work. - Develop further the BME Staff Network group to encourage a group that is owned by BME staff within the workforce to identify actions to change BME staffs experience - Arrange an event in partnership with other NHS employers in the area with NHS England WRES team specifically for BME staff to encourage a commitment to the BME Staff Network | Narrow the gap in the relative likelihood of white staff being treated differently compared to BME staff in the staff survey results for 2017 | Freedom to Speak up Guardian & HR Manager | Completed by March 2019 Completed by March 2019 |